## Initial Plan
Title | 100K Years War
Description | 2-player turn-based spaceship fleet combat strategy game that takes place on a 3D cube grid
Team Breakdown | Josh as Designer, Sound Designer, Programmer | Chang as Artist | C.J. as Lead Programmer
Week Plan
9 | System framework, art and sound asset lists, design document
10 | Technical demo w/keyboard controls, 3 spaceship models, sounds, level design
11 | Playable game, test gamepad controls, textures, UI design, music
12 | Iterate on design, lighting, polish UI, bug fixes
13 | Iterate on design, bug fixes
Requests for Training | Textures and materials
Subversion Address | https://nyugamecenter.sourcerepo.com/nyugamecenter/Game_Studio_I/joshuaraab/100K Years War
iTween, Oren-rJayer (shader)

## Task List
Task | Priority | Category | Owner | Status | Notes
System Architecture and Document | 1 | Doc | CJ | In progress |  | 1 | Josh | In progress
Full System Structure details into function block | 1 | Doc | CJ | In progress |  | 2 | Chang | Done
Finish ship models | 1 | Models | Chang | Finished |  | 3 | CJ
In-game music | 1 | Audio | Josh | In progress |  | 4
Implement turn structure | 1 | Code | CJ |  |  | 5
Implement ship rotation | 1 | Code | CJ
Design ship rotation stuff (movement, firing range, armor) | 1 | Design | Josh
Lasers | 2 | Art | Chang | In Progress
Level design - ship deployments | 2 | Design | Josh |  | Use placeholder models for ships for now
Position cameras better | 2 | Camera | CJ
Implement ship selection and movement | 2 | Code | CJ
Implement attacking | 2 | Code | CJ
Implement game structure (rounds) | 3 | Code | CJ
Implement victory conditions | 3 | Code | CJ
Procedure for generating debris | 3 | Code | Josh |  | Parameters: size of field (in 3 dimensions), density of debris
Procedure for generating asteroid field | 3 | Code | Josh |  | Parameters: size of field (in 3 dimensions), size of asteroids, number of asteroids
Experiment with ship stats | 3 | Design | Josh
Experiment with map size | 3 | Design | Josh
Implement debris rules | 3 | Code | CJ |  | Costs 3 movement points to enter
Lines for the cubes not faces | 4 | Materials | CJ | Hold
Level design - terrain | 4 | Design | Josh
Done
Camera Position Function | 2 | Function | CJ | Done
Indicator Function | 2 | Function | CJ | Done
Implement ship stats | 1 | Code | Josh | Done

## Art Asset List
Asset | Asset Type | Status | Notes
Spaceships
3D Model - Chevalier Class | 3D Model | Cpmpleted | Big "knight" ship - fast, powerful, well armored
3D Model - Halberd Class | 3D Model | Completed | Medium sized "infantry" ship - powerful + well-armored, but slow
3D Model - Yeoman Class | 3D Model | Completed | Small "archer" ship - fast, long-range, good rate of fire, but weak
Texture - Chevalier Class (Entente) | Texture |  | Blue texture for Chevalier Class
Texture - Halberd Class (Entente) | Texture |  | Blue texture for Halberd Class
Texture - Halberd Class (Federation) | Texture |  | Red texture for Halberd Class
Texture - Yeoman Class (Entente) | Texture |  | Blue texture for Yeoman Class
Texture - Yeoman Class (Federation) | Texture |  | Red texture for Yeoman Class
Lasers
Laser - Chevalier (Entente) | Line Renderer | In Progress | Big blue laser - note: there is no Anglian (red) Chevalier
Laser - Halberd (Entente) | Line Renderer | In Progress | Mid-sized blue laser
Laser - Halberd (Federation) | Line Renderer | In Progress | Mid-sized red laser
Laser - Yeoman (Entente) | Line Renderer |  | Little blue laser
Laser - Yeoman (Federation) | Line Renderer |  | Little red laser
Planet |  | Finished
Planet | 3D Model | Finished | The battle is fought over this planet, Agincourt-15
Planetary Shield | Particles (?) | In progress | The planet is surrounded by a shield takes damage from the attacker's ships - if it is destroyed, attacker wins
Terrain
Asteroid | 3D Model | completed | Big rock that blocks movement
Debris | 3D Model | completed | Smaller floating space stuff - slows down ships that move through it
Background
Space background | Skybox (?) |  | Background of game
UI
2D game overlay | Overlay |  | Always on Includes: --Whose turn it is (Anglian Federation, Entente Nouveau) --Round number (ex. "Round 8/10") --Strength of planetary shield (ex. "Planetary Shield: 8000/15000")
2D ship stats overlay | Overlay |  | Appears when ship is highlighted Includes: --Ship icon (small version of model) --Ship class (Chevalier Class, Halberd Class, Yeoman Class) --Team (Anglian Federation, Entente Francophone) --Stats (Hull Strength, Power, Armor, Firing Rate, Range, Speed
2D fire/wait pop-up menu | Menu |  | Appears after choosing place for ship to end up Menu: Includes "Fire" and "Wait" options
Screens
Title Screen |  |  | Includes: Game title (100K Years War: Agincourt), our names, some graphic, text that says how to start game
End Screen |  |  | Includes: Winner, method of victory, stats (ships destroyed by each side), text that says how to restart game Methods of victory: --Annihilation (enemy team has no ships left) --Submission (planetary shield destroyed) --Resistance (after 10 rounds passed, planetary shield is not destroyed and Anglian Federation still has at least 1 ship)

## Sound Asset List
Asset | Asset Type | Status | What Plays It? | Notes
Music
Title screen music | Music | Created | Camera
In-game music | Music | In game | Camera
End screen music | Music |  | Camera
General SFX
Confirm | SFX | Created | Indicator | For use on title screen and end screen
Select chevalier | SFX | In game | Indicator | Record new sounds
Select yeoman | SFX | In game | Indicator | Record new sounds
Select halberd | SFX | In game | Indicator | Record new sounds
Switch target | SFX | In game | Indicator
Enter attack mode | SFX | In game | Indicator
Enter move mode | SFX | In game | Indicator
Invalid | SFX | In game | Indicator | No targets in range Cannot move forward
Turn start | SFX | Created | Indicator | In game???
Camera switch |  | In game | Camera
Movement SFX
Rotate | SFX | In game | Indicator
Move forward | SFX | In game | Indicator
Pass | SFX | In game | Indicator
Combat SFX
Fire laser | SFX | In game | Ship
Ship damaged | SFX | In game | Ship
Ship destroyed | SFX | In game | Ship
Planetary shield damaged | SFX | In game | Planet | Just using the same as ships for now
Planetary shield destroyed | SFX | In game | Planet | Just using the same as ships for now

## Input Scheme
Key | Effect 1 | Effect 2 | Effect 3
W | Move indicator up
S | Move indicator down
A | Move indicator left
D | Move indicator right
Q | Move indicator forward
E | Move indicator backward
Enter | Lock onto currently selected ship | Fire on currently selected target | Confirm
Backspace | Break lock (i.e. deselect) | Cancel
L | Toggle to next available ship | Toggle to next available target within range